## Implementation Tracker
EVERMORE LIFE — MASTER IMPLEMENTATION TRACKER
✅ COMPLETE ¦ 🔵 IN PROGRESS (next up) ¦ 🟡 YOU DO IT (requires your account/action) ¦ 📁 FILE READY
Last updated: May 1, 2026 ¦ Steps 1–5 COMPLETE ✅ ¦ Step 6 IN PROGRESS 🔵 ¦ Steps 7–10 queued
# | TASK / DELIVERABLE | STATUS | WHAT TO DO / FILE LOCATION
🚀 DEPLOYMENT — STEPS 1–5 (ALL COMPLETE ✅)
1 | KVN deployed to Cloudflare Workers ✅ | ✅ COMPLETE | COMPLETE — May 1, 2026 Live URL: kvn-agent.newmexicomarketingpartners.workers.dev KVN AI agent live and accessible from any device.
2 | Sarah AI deployed to Cloudflare Workers ✅ | ✅ COMPLETE | COMPLETE — May 1, 2026 Live URL: sarah-evermore.newmexicomarketingpartners.workers.dev Sarah's virtual office live and reachable.
3 | Claude API (Haiku) hardwired into Sarah ✅ | ✅ COMPLETE | COMPLETE — May 1, 2026 Model: claude-haiku-4-5 Sarah now gives real AI-powered responses. Promise-resolution bug fixed. Sarah blue screen bug resolved.
4 | GHL Private Integration Token + Location ID injected into Sarah ✅ | ✅ COMPLETE | COMPLETE — May 1, 2026 GHL API token and Location ID injected via wire_ghl_webhook.sh Sarah pushes leads directly to GoHighLevel CRM on every booking. Redeployed to Cloudflare after injection.
5 | Meta Pixel ID 1895928277755643 installed in landing page ✅ | ✅ COMPLETE | COMPLETE — May 1, 2026 Pixel ID: 1895928277755643 Tracking events: PageView + Lead Landing page CTA updated to 'See If You Qualify' $1/day pricing removed. Sarah CSS portrait added.
🔵 STEP 6 — GOHIGHLEVEL PIPELINE SETUP (IN PROGRESS)
6a | GHL pipeline: 'Final Expense Leads' — 9 stages | 🔵 IN PROGRESS | NEXT ACTION: Run setup_ghl_pipeline.sh OR manually create in GHL: Stages: New Lead (Sarah AI) → Contacted Attempt 1 → Contacted Attempt 2 → Appointment Set → Appointment Confirmed → On Call → Closed Won ✅ → Closed Lost ❌ → Nurture In GHL: CRM → Pipelines → Create New Pipeline → 'Final Expense Leads'
6b | GHL consultation calendar — 15-min free consultation slots | 🔵 IN PROGRESS | NEXT ACTION: In GHL → Calendars → + Create Calendar Name: 'Evermore Life Free Consultation' Duration: 15 min ¦ Buffer: 15 min Hours: Mon–Fri 9am–6pm, Sat 10am–2pm Toggle ON: auto-confirmation email + 24hr reminder Copy booking link → paste into Sarah INTEGRATION POINT 3
6c | GHL custom contact fields (11 fields) | 🔵 IN PROGRESS | NEXT ACTION: GHL → Settings → Custom Fields → + Add Field (Contact) Fields to create: Insurance Topic (Dropdown), Age (Number), Health Rating (Dropdown), Coverage Goal (Text), Beneficiary (Text), Smoker (Dropdown: Yes/No), State (Text), UTM Source, UTM Medium, UTM Campaign, Lead Source See GHL_Setup_Guide.docx Section 3 for full field specs
⏳ STEP 7 — META ADS CAMPAIGNS (QUEUED)
7 | Meta Business Manager — create TOF/MOF/BOF ad campaigns | ⏳ QUEUED | AFTER Step 6: In Meta Ads Manager → create 3 campaigns: Campaign 1: Video Views (TOF) — $15/day, 3 ad sets Campaign 2: Lead Generation (TOF) — $15/day Campaign 3: Traffic to Sarah page — $10/day Full ad set specs: Evermore_Meta_Funnel_Playbook.xlsx → Tab 3
⏳ STEP 8 — RECORD VIDEO AD A (QUEUED)
8 | Record Video Ad A — hero 60–90 sec video | ⏳ QUEUED | Script ready in: Evermore_Video_Ad_Scripts.docx Record on iPhone or hire UGC creator (Billo.app or Fiverr) Edit in CapCut (free) — auto-captions built in Compliance line must be included (see script)
⏳ STEP 9 — GENERATE AD IMAGES (QUEUED)
9 | Generate ad images using AI image prompts | ⏳ QUEUED | Prompts ready in: Evermore_Meta_Funnel_Playbook.xlsx → Tab 5 10 image prompts ready to paste into Midjourney / DALL-E 3 / Adobe Firefly Add text overlays in Canva (free) After images generated: upload to Meta Ads Manager
⏳ STEP 10 — PRIVACY POLICY PAGE (QUEUED)
10 | Privacy policy page — link in landing page footer | ⏳ QUEUED | Generate at: Termly.io (free) Meta REQUIRES privacy policy for lead ads — do before launching campaigns Add link to footer of Evermore_Landing_Page.html Redeploy landing page after adding link
SARAH AI ASSISTANT — FRONT-END
S1 | Sarah AI — Virtual office, chat, booking, confirmation | ✅ COMPLETE | COMPLETE ✅ File: Sarah_Evermore_AI.html Deployed: sarah-evermore.newmexicomarketingpartners.workers.dev
S2 | Claude API (Haiku) — real AI responses | ✅ COMPLETE | COMPLETE ✅ — Step 3 done Model: claude-haiku-4-5 hardwired AI-powered responses live.
S3 | Meta Pixel ID installed (PageView + Lead events) | ✅ COMPLETE | COMPLETE ✅ — Step 5 done Pixel ID: 1895928277755643 Events firing: PageView, Lead
S4 | GHL integration — Sarah pushes leads to CRM | ✅ COMPLETE | COMPLETE ✅ — Step 4 done GHL Private Integration Token + Location ID injected Leads flow to GoHighLevel on every booking submit
S5 | Landing page CTA + UI updates | ✅ COMPLETE | COMPLETE ✅ — Step 5 done CTA changed to: 'See If You Qualify' $1/day removed from copy Sarah CSS portrait added
S6 | GHL calendar wired to Sarah booking (INTEGRATION POINT 3) | 🔵 IN PROGRESS | NEXT: After Step 6b calendar is created → paste GHL calendar link into Sarah In Sarah_Evermore_AI.html: find INTEGRATION POINT 3 → replace placeholder with GHL calendar booking URL
KVN — INTERNAL AGENT
K1 | KVN deployed to Cloudflare Workers | ✅ COMPLETE | COMPLETE ✅ — Step 1 done Live URL: kvn-agent.newmexicomarketingpartners.workers.dev
K2 | KVN — Wire to Claude API for real intelligence | 🟡 YOU DO IT | YOU DO IT: 1. In KVN.html find the keyword-based chat handler 2. Replace with fetch() to Anthropic API 3. Use same API key already wired into Sarah KVN system prompt already written in the file.
K3 | KVN — Daily briefing mode | 🟡 YOU DO IT | Future build — needs Google Calendar API or manual schedule input. Tell Claude when you're ready to build this.
META ADS — CONTENT & COPY
M1 | Video Ad A script (Hero / 60–90 sec) | 📁 FILE READY | File: Evermore_Video_Ad_Scripts.docx Teleprompter-ready script complete.
M2 | Video Ad B–E scripts (retargeting) | 📁 FILE READY | File: Evermore_Video_Ad_Scripts.docx All 4 retargeting scripts complete.
M3 | All image ad copy (10 ads — primary text, headlines, CTAs) | 📁 FILE READY | File: Evermore_Meta_Funnel_Playbook.xlsx → Tab 4 10 ads fully written.
M4 | AI image generation prompts (10 ads) | 📁 FILE READY | File: Evermore_Meta_Funnel_Playbook.xlsx → Tab 5 Ready to paste into Midjourney/DALL-E.
M5 | Record Video Ad A (the hero 60–90 sec video) | 🟡 YOU DO IT | YOU DO IT (Step 8): Script in Evermore_Video_Ad_Scripts.docx Record on iPhone or hire UGC creator on Billo.app Edit in CapCut — auto-captions built in
M6 | Generate ad images using AI prompts | 🟡 YOU DO IT | YOU DO IT (Step 9): 1. Open Evermore_Meta_Funnel_Playbook.xlsx → Tab 5 2. Copy each prompt → paste into Midjourney / DALL-E 3 3. Add text overlays in Canva
GOHIGHLEVEL CRM
G1 | GHL Private Integration Token injected into Sarah | ✅ COMPLETE | COMPLETE ✅ — Step 4 done Token injected via wire_ghl_webhook.sh Sarah pushes contacts to GHL API on every booking.
G2 | GHL pipeline: Final Expense Leads (9 stages) | 🔵 IN PROGRESS | IN PROGRESS — Step 6a See GHL_Setup_Guide.docx Section 2 All 9 stage names defined and ready to create.
G3 | GHL custom contact fields (11 fields) | 🔵 IN PROGRESS | IN PROGRESS — Step 6c See GHL_Setup_Guide.docx Section 3
G4 | GHL calendar: Free Consultation 15 min | 🔵 IN PROGRESS | IN PROGRESS — Step 6b See GHL_Setup_Guide.docx Section 6
G5 | GHL automation: New Lead Flow (SMS + notifications) | 🟡 YOU DO IT | YOU DO IT (after Step 6): See GHL_Setup_Guide.docx Section 5 SMS templates ready in GHL_SMS_Email_Templates.docx
G6 | GHL + Meta Pixel Conversions API | 🟡 YOU DO IT | YOU DO IT: GHL Settings → Integrations → Facebook → Connect Enter Pixel ID: 1895928277755643 See GHL_Setup_Guide.docx Section 7
COMPLIANCE & LEGAL
C1 | Ad compliance language in all scripts | ✅ COMPLETE | COMPLETE ✅ All scripts include: 'Not affiliated with any government program. Licensed insurance agent. Coverage and rates vary by age and health.'
C2 | Sarah — no specific coverage promises | ✅ COMPLETE | COMPLETE ✅ Sarah uses ranges only: 'Most clients in your situation qualify for...'
C3 | Privacy policy page | ⏳ QUEUED | QUEUED — Step 10 Generate at Termly.io (free) Required by Meta before launching lead ads Add link to Evermore_Landing_Page.html footer
C4 | State licensing verification | 🟡 YOU DO IT | YOU DO IT: Verify license in every state you advertise Add NPN to GHL agent profile Check NIPR.com